## Claims
Claim ID | Claim / evidence-bounded conclusion | Status | Source ID(s) | Section(s), in source order | Qualification / guardrail
C01 | Pilot target is Dec 8. | FACT — documented target, not a commitment | S1 | §1 | Target only; vendor cannot guarantee Dec 8 (S3 §2).
C02 | Proposed budget ceiling is EUR12,000. | PROPOSAL — ceiling | S1 | §1 | Not an approved budget; approval is pending in the brief.
C03 | Approval is pending. | FACT — pending approval | S1 | §1 | Do not treat the brief as authorization.
C04 | Customer training is required. | FACT — requirement | S1 | §2 | Training is also included in the quote (S3 §1).
C05 | Travel/tax treatment is not decided. | UNKNOWN — explicitly unresolved | S1 | §2 | No approved treatment is supplied.
C06 | Dec 15 is proposed instead of the earlier target. | PROPOSAL — explicitly NOT approved | S2 | §1 | Does not establish a confirmed pilot date.
C07 | Finance proposes EUR9,500. | PROPOSAL — explicitly NOT approved | S2 | §1 | Not an approved ceiling or quoted price.
C08 | Mina will check the vendor quote. | FACT — recorded action | S2 | §2 | Only this action has a named owner in the excerpts.
C09 | No deadline is assigned to Mina’s quote check. | UNKNOWN — no deadline assigned | S2 | §2 | Nov 15 is quote validity, not Mina’s deadline (S3 §1).
C10 | Vendor quote amount is EUR10,200. | FACT — quoted price | S3 | §1 | Not an approved budget or all-in cost.
C11 | The vendor quote includes training. | FACT — quoted scope | S3 | §1 | Matches the stated training requirement (S1 §2); adequacy is not established.
C12 | The vendor quote excludes tax and travel. | FACT — exclusions | S3 | §1 | Do not infer a total including these items.
C13 | The vendor quote is valid through Nov 15. | FACT — stated validity endpoint | S3 | §1 | No year/current date assumed; not a task deadline.
C14 | Vendor cannot guarantee Dec 8. | FACT — delivery limitation | S3 | §2 | Do not interpret the target as a vendor commitment.
C15 | Vendor has no commitment for Dec 15. | FACT — no commitment | S3 | §2 | Does not prove Dec 15 is impossible; it remains uncommitted.
C16 | No approved budget is established by the supplied excerpts. | UNKNOWN — evidence gap | S1; S2 | §1; §1 | Inference limited to these excerpts; both budget amounts remain proposals.
C17 | All-in cost is not established by the supplied excerpts. | UNKNOWN — evidence gap | S1; S3 | §2; §1 | Treatment is undecided and quote excludes tax/travel; no invented total.
C18 | No approved, vendor-committed pilot date is established by the excerpts. | UNKNOWN — evidence gap | S1; S2; S3 | §1; §1; §2 | Dec 8 is a target; Dec 15 is unapproved; vendor commitments are absent.

## Questions
Question ID | Unresolved question | Status | Source / section basis | Related claims | Action
Q01 | Which pilot date should be approved, and can the vendor commit to it? | UNKNOWN | S1 §1; S2 §1; S3 §2 | C01, C06, C14, C15, C18 | A01
Q02 | What budget ceiling, if any, will be approved? | UNKNOWN | S1 §1; S2 §1 | C02, C03, C07, C16 | A02
Q03 | How will tax and travel be treated and funded, and what is the all-in cost? | UNKNOWN | S1 §2; S3 §1 | C05, C10, C12, C17 | A03
Q04 | What deadline should be assigned to Mina’s quote check? | UNKNOWN — no deadline assigned | S2 §2; S3 §1 | C08, C09, C13 | A04
Q05 | Does the included training meet the customer requirement? | UNKNOWN — adequacy not stated | S1 §2; S3 §1 | C04, C11 | A05
Q06 | Will quote renewal or revalidation be needed when approval is sought? | UNKNOWN — current validity not inferred | S3 §1 | C13 | A06

## Next actions
Action ID | Proposed next action | Status | Owner status | Deadline status | Source / section basis | Question
A01 | Seek explicit date approval and a written vendor delivery commitment. | PROPOSAL | Owner not assigned in excerpts | Deadline not assigned in excerpts | S1 §1; S2 §1; S3 §2 | Q01
A02 | Resolve the two budget proposals and document one approved ceiling. | PROPOSAL | Owner not assigned in excerpts | Deadline not assigned in excerpts | S1 §1; S2 §1 | Q02
A03 | Clarify tax/travel treatment and obtain an itemized all-in cost before approval. | PROPOSAL | Owner not assigned in excerpts | Deadline not assigned in excerpts | S1 §2; S3 §1 | Q03
A04 | Complete Mina’s recorded quote check; explicitly agree a deadline separately from quote validity. | PROPOSAL — execution and deadline clarification | Mina for quote check only (S2 §2) | No assigned deadline (S2 §2); Nov 15 is quote validity (S3 §1) | S2 §2; S3 §1 | Q04
A05 | Confirm that the quoted training satisfies the customer requirement. | PROPOSAL | Owner not assigned in excerpts | Deadline not assigned in excerpts | S1 §2; S3 §1 | Q05
A06 | Check quote validity at the decision point; seek renewal if needed. | PROPOSAL | Owner not assigned in excerpts | Deadline not assigned in excerpts | S3 §1 | Q06

## Source excerpts
Source ID | Source title | Section | Date (year not supplied) | Supplied excerpt
S1 | Project brief | §1 | Nov 1 | pilot target Dec 8, proposed budget ceiling EUR12000, approval pending.
S1 | Project brief | §2 | Nov 1 | customer training required; travel/tax treatment not decided.
S2 | Meeting minutes | §1 | Nov 3 | Dec 15 proposed instead, NOT approved; finance proposes EUR9500, also NOT approved.
S2 | Meeting minutes | §2 | Nov 3 | Mina will check the vendor quote; no deadline assigned.
S3 | Vendor quote | §1 | Nov 4 | EUR10200 includes training, excludes tax and travel; valid through Nov15.
S3 | Vendor quote | §2 | Nov 4 | vendor cannot guarantee Dec8; no commitment for Dec15.