## Claims
Claim ID | Claim / historical evidence | Current status / history | Original source ID(s) | Section(s), in source order | Current qualification / superseding evidence
C01 | Pilot target is Dec 8. | FACT — historical target; no date approved | S1 | §1 | Dec 8 remains a documented target (S1 §1), not an approved date (S4 §1) or vendor commitment (S3 §2).
C02 | Proposed budget ceiling is EUR12,000. | PROPOSAL — SUPERSEDED for ceiling-setting | S1 | §1 | S4 §1 approves EUR11,000 excluding tax/travel; replaces this EUR12,000 ceiling proposal. Historical excerpt retained.
C03 | Approval is pending. | FACT — historical pending approval | S1 | §1 | Budget-ceiling uncertainty resolved by S4 §1 only. No pilot date approved (S4 §1); not blanket project/purchase approval.
C04 | Customer training is required. | FACT — requirement | S1 | §2 | Training is also included in the quote (S3 §1).
C05 | Travel/tax treatment is not decided. | UNKNOWN — explicitly unresolved | S1 | §2 | No approved treatment is supplied.
C06 | Dec 15 is proposed instead of the earlier target. | PROPOSAL — still unapproved date alternative | S2 | §1 | S4 §1 approves no pilot date. Do not label this date proposal approved or superseded by an approved date.
C07 | Finance proposes EUR9,500. | PROPOSAL — SUPERSEDED for ceiling-setting | S2 | §1 | S4 §1 approves EUR11,000 excluding tax/travel; replaces finance’s EUR9,500 budget proposal. Historical excerpt retained.
C08 | Mina will check the vendor quote. | FACT — recorded action | S2 | §2 | Only this action has a named owner in the excerpts.
C09 | No deadline is assigned to Mina’s quote check. | UNKNOWN — historical; NOW RESOLVED | S2 | §2 | No deadline was assigned in S2 §2; S4 §2 now requires completion by Nov 10. Nov 15 remains quote validity (S3 §1).
C10 | Vendor quote amount is EUR10,200. | FACT — quoted price | S3 | §1 | Not an approved budget or all-in cost.
C11 | The vendor quote includes training. | FACT — quoted scope | S3 | §1 | Matches the stated training requirement (S1 §2); adequacy is not established.
C12 | The vendor quote excludes tax and travel. | FACT — exclusions | S3 | §1 | Do not infer a total including these items.
C13 | The vendor quote is valid through Nov 15. | FACT — stated validity endpoint | S3 | §1 | No year/current date assumed; not a task deadline.
C14 | Vendor cannot guarantee Dec 8. | FACT — delivery limitation | S3 | §2 | Do not interpret the target as a vendor commitment.
C15 | Vendor has no commitment for Dec 15. | FACT — no commitment | S3 | §2 | Does not prove Dec 15 is impossible; it remains uncommitted.
C16 | No approved budget is established by the supplied excerpts. | UNKNOWN — historical; NOW RESOLVED | S1; S2 | §1; §1 | Earlier evidence gap resolved by S4 §1: approved ceiling EUR11,000 excluding tax/travel. Not purchase approval.
C17 | All-in cost is not established by the supplied excerpts. | UNKNOWN — evidence gap | S1; S3 | §2; §1 | Treatment is undecided and quote excludes tax/travel; no invented total.
C18 | No approved, vendor-committed pilot date is established by the excerpts. | UNKNOWN — still unresolved | S1; S2; S3 | §1; §1; §2 | S4 §1 expressly approves no pilot date; S3 §2 supplies no guarantee for Dec 8 or commitment for Dec 15.
C19 | Management approves a budget ceiling of EUR11,000 excluding tax and travel. | FACT — approved ceiling | S4 | §1 | Current ceiling; supersedes C02/C07 for ceiling-setting. Does not establish all-in cost, vendor selection or purchase approval.
C20 | Mina must finish the quote check by Nov 10. | FACT — required action and deadline | S4 | §2 | Resolves C09. Does not establish task completion. Nov 15 remains quote validity (S3 §1).
C21 | No pilot date is approved. | FACT — explicitly unapproved | S4 | §1 | Dec 8 target and Dec 15 alternative are not approved. Vendor limitations remain (S3 §2).
C22 | Vendor selection, purchase approval and a delivery commitment are not established by these excerpts. | UNKNOWN — authorization/evidence boundary | S4; S3 | §1–§2; §2 | Evidence-bounded conclusion: S4 states a ceiling and quote-check deadline only; S3 has no date commitment. Not proof of any external decision.

## Questions
Question ID | Question | Current status | Source / section basis | Related claims | Action | Resolution / remaining gap
Q01 | Which pilot date will be approved, and can the vendor commit to it? | UNRESOLVED — date and vendor commitment | S1 §1; S2 §1; S3 §2; S4 §1 | C01, C06, C14, C15, C18, C21 | A01 | S4 explicitly approves no pilot date; vendor commitment is still absent.
Q02 | What budget ceiling, if any, will be approved? | NEWLY RESOLVED — ceiling only | S1 §1; S2 §1; S4 §1 | C02, C07, C16, C19 | A02 | EUR11,000 excluding tax and travel approved in S4 §1; not an all-in cost or purchase approval.
Q03 | How will tax and travel be treated/funded, and what is the all-in cost? | UNRESOLVED — exclusions do not resolve treatment | S1 §2; S3 §1; S4 §1 | C05, C12, C17, C19 | A03 | Both ceiling and quote exclude tax/travel; treatment and total remain unresolved.
Q04 | What deadline should be assigned to Mina’s quote check? | NEWLY RESOLVED — deadline only | S2 §2; S4 §2; S3 §1 | C08, C09, C20 | A04 | Mina must finish by Nov 10. Completion not established; Nov 15 is quote validity only.
Q05 | Does included training meet the customer requirement? | UNRESOLVED — adequacy not stated | S1 §2; S3 §1 | C04, C11 | A05 | Requirement and quote inclusion are known; adequacy is not confirmed.
Q06 | Will quote renewal or revalidation be needed at decision time? | UNRESOLVED — validity check still needed | S3 §1; S4 §2 | C13, C20 | A06 | Quote valid through Nov 15; Nov 10 task deadline does not renew or validate the quote.

## Next actions
Action ID | Action | Status / authority | Owner status | Deadline status | Source / section basis | Question status
A01 | Seek explicit pilot-date approval and a written vendor delivery commitment. | PROPOSAL — still open | Owner not assigned in excerpts | Deadline not assigned in excerpts | S1 §1; S2 §1; S3 §2; S4 §1 | Q01
A02 | Record the approved EUR11,000 ceiling excluding tax/travel; archive EUR12,000 and EUR9,500 as superseded proposals. | PROPOSAL — record resolved ceiling | Owner not assigned in excerpts | Deadline not assigned in excerpts | S1 §1; S2 §1; S4 §1 | Q02 — newly resolved
A03 | Clarify tax/travel treatment and funding; obtain itemized all-in cost. | PROPOSAL — still open | Owner not assigned in excerpts | Deadline not assigned in excerpts | S1 §2; S3 §1; S4 §1 | Q03
A04 | Finish the vendor quote check by Nov 10. | REQUIRED — S4 instruction; completion unknown | Mina (S2 §2; S4 §2) | Nov 10 (S4 §2); not Nov 15 quote validity (S3 §1) | S2 §2; S4 §2; S3 §1 | Q04 — deadline newly resolved
A05 | Confirm quoted training satisfies the customer requirement. | PROPOSAL — still open | Owner not assigned in excerpts | Deadline not assigned in excerpts | S1 §2; S3 §1 | Q05
A06 | Check quote validity at decision time; seek renewal if needed. | PROPOSAL — still open | Owner not assigned in excerpts | Deadline not assigned in excerpts; quote valid through Nov 15 (S3 §1) | S3 §1; S4 §2 | Q06

## Source excerpts
Source ID | Source title | Section | Date (year not supplied) | Supplied excerpt
S1 | Project brief | §1 | Nov 1 | pilot target Dec 8, proposed budget ceiling EUR12000, approval pending.
S1 | Project brief | §2 | Nov 1 | customer training required; travel/tax treatment not decided.
S2 | Meeting minutes | §1 | Nov 3 | Dec 15 proposed instead, NOT approved; finance proposes EUR9500, also NOT approved.
S2 | Meeting minutes | §2 | Nov 3 | Mina will check the vendor quote; no deadline assigned.
S3 | Vendor quote | §1 | Nov 4 | EUR10200 includes training, excludes tax and travel; valid through Nov15.
S3 | Vendor quote | §2 | Nov 4 | vendor cannot guarantee Dec8; no commitment for Dec15.
S4 | Approval note | §1 | Nov 5 | management approves a budget ceiling of EUR11000 excluding tax and travel; no pilot date is approved.
S4 | Approval note | §2 | Nov 5 | Mina must finish the quote check by Nov 10.